## Tasks
Data or Product | Time | Agency | Cost | Comments 2018 | Status 04/05/2019
Updated landslide inventory with overlay events | 2017 | USFS (J.F and D.L) | In house |  | Landslide layer has two feature classes, one is a polygon, the other is a best guess of initiation points. Both are available on data.gov
NetMap (with Miller model) landslide initiation and runout modeling | 2018 | USFS: (D.L., J.F., or A.J.) | $10k (contractor) | Lidar acquision is a prerequisite | Netmap landslide hazard map should be available sometime mid-summer. Terrainworks will build a synthetic stream network and identify confluence zones. The results will be compared with landslide mapping for the area. It will show initiation and runout in one product.
Detailed soil maps | 2022 | USFS (J.F) DGGS | No funds identified | Prioritize catchment areas
ArcGIS online app |  | USFS (J.F.) |  |  | Would allow everyone with study sites in Sitka to share locations with each other.
Soil depth measurements |  | USFS (K.P.), SSSC | $10k (Paid for) |  | Would allow the employment of 2 high school students for field experience. Funds allocated, waiting on approval of agreement.
Identify three possible sites for weather station at Gavin or Harbor Mountain | 2017 | USFS: A.P. DGGS: G.W. | In house | in progress
Install stream gagues and developing rating curve- Starrigavan and Cascade Cr. | 2017 (S) 2018 (CC) | NWS (A.J.) STA (J.H.) USFS (K.P.) | NWS installation and maintanence ($ TBD) STA personnel to help develop rating curve by taking flow measurements | Need to look at permits from USFS and city to insall gages on bridges before installing | NWS: Starrigavin gauges are up and running, stable as of 04/04/2019. Will be up on the webpage in the next couple of weeks.
Coupled hydrological/landslide model running in real time | in progress 2023 | NWS (A.J.) DGGS (R.W.) | In house | Research effort hydrological model sooner
Install weather station at higher elevation (existing equipment available) | 2018 | DGGS: G.W. USFS: permitting CBS: maintenance | Upgraded: $5k Installation: $20k Maint: $4k/yr | Permitting needed ASAP | USFS: Weather station permitting is nearing completion in conversations with Ronnie, then it's a 6 month processing for permitting.
Targeted repeat laser scans of potential debris-flow source areas | 11/17-5/18 | DGGS/G.W. | Ad hoc if funds available | Repeat at 2-year intervals | Funding required.
App to involve citizen science for reporting landslides: promotion | 2018 | DGGS (G.W.) SSSC CBS RAND | $5k-$10k | Modified for fishermen/hikers/hunters (Mountain Hub, LEO) | App was purchased my Mammut, put this project on hold. Mammut has accepted the project and this project can continue moving forward.
A homewoner's guide to landslides | 2018 | DGGS (G.W./R.D.) CBS (M. Bosak) |  |  | Hasn't been addressed yet, there was pushback until it was funded.
DGGS Hazard Mapping (new lidar from NPS) | 2018 | DGGS/R.D. (USFS) | Paid for | Get boring logs and landslide inventory | Landslide hazard mapping is done, in the hands of the City of Sitka.
Soil moisture sensors and monitoring (radio network) (Research) | 2019 | USGS (R.B.) DGGS USFS/PNWRS (A.J., J.F.) | $117k equipment. Labor, maintainance, and monitoring extra | Source location in initiation zone (water table) three hollows
Create rainfall intensity and duration curves for existing information | 2018 | NWS (A.J.) USGS (R.B.) USFS (K.K.P) | In house | Add smaller slides to inventory slides (USFS) | Completed prelim. looking at data (slides from FS database, events described by jacquie and others). Put together prelim intensity duration threshold and plans to return to it this summer.
Establish rainfall runoff (stream gague) rating curves for Indian River | 2019 | NPS (B.C.) USGS, NWS (A.J.), STA (J.H.) | USGS contracted by NPS | USGS has a published rate curve for Indian River
Real time SNOTEL - ask NRCS (could be higher priority if available) | 2018 | NPS (B.C.) NWS (A.J.), USFS DGGS (G.W.) | $35k install- maintainance TBD | Indian River head waters, permitting USFS
Improve radar use from Biorka flash flood monitoring program | 2019 | NWS (A.J.) | In house
Gather local people with knowledge of previous landslides (contractors, city crew, journalist) | 2018 | SSSC (L.B.) RAND USFS (A.J.) S&W (B.L.) | ? | Landslide deposition locations
Three additional weather stations |  | DGGS, NWS, CBS | $50kx3 = $150k | Do permitting now
Blue lake height and connecting NWS | 2018 | CSB (D. Tadic) NWS |  | IT folks

## Contacts
Name | Agency | Title | Email | Location
Megan Bosak | CBS | Community Affairs Director | maegan.bosak@cityofsitka.org | Sitka, AK
Micharl Harmon | CBS | Director Public Works | michael@cityofsitka.com | Sitka, AK
Gabriel Wolken | DGGS | Research Scientist | gabriel.wolken@alaska.gov | Fairbanks, AK
Ronald Daanen | DGGS | Geohydrologist | ronald.daanen@alaska.gov | Fairbanks, AK
Chad Hults | NPS | Alaska Regional Geologist | chad_hults@nps.gov | Anchorage, AK
Brinnen Carter | NPS, Sitka | Chief of Natural Resources | brinnen_carter@nps.gov | Sitka, AK
Aaron Jacobs | NWS | Senior Service Hydrologist | aaron.jacobs@noaa.gov | Juneau, AK
Joel Curtis | NWS | Warning Coordination Meteorolo | joel.curtis@noaa.gov | Juneau, AK
Miriam Marlier | RAND | Associated Physical Scientist | mmarlier@rand.org | Santa Monica, CA
Robert Lempert | RAND | Policy Analyst | lempert@rand.org | Santa Monica, CA
Ryan Brown | RAND | Senior Social and Behavioral Researcher | rbrown@rand.org | Santa Monica, CA
Bill Laprade | Shannon & Wilson | Vide-President | wtl@shanwil.com | Seattke, WA
Lisa Busch | SSSC | Executive Director | lbusch@sitkascience.org | Sitka, AK
Cora Siebert | SSSC | Geoscience Coordinator | csiebert@sitkascience.org | Sitka, AK
Anne Davis | STA | Administrative Services Director | anne.davis@sitkatribe-nsn.gov | Sitka, AK
Jeff Feldspauch | STA | Resources Protection Director | jeff.feldspauch@sitkatribe-nsn.gov | Sitka, AK
Jenn Hamblen | STA | Fishery Biologist | jennifer.hamblen@sitkatribe-nsn.gov | Sitka, AK
Joe Trainor | Udel DRC | Program Director | jtrainor@udel.edu
Brian Buma | Universituof Colorado | Professor, ecology & landscape change | brian.buma@ucdenver.edu | Denver, CO
Kyle Turchick | University of Colorado | Grad Student of Brian Buma | KYLE.TURCHICK@UCDENVER.EDU> | Denver, CO
Josh Roering | University of Oregon | Professor, geomorphology, surface processes | jroering@uoregon.edu | Eugene, OR
Adam Booth | University of Oregon | Professor, geomorphology, surface processes | boothad@pdx.edu | Portland, OR
Aaron Prussian | USFS | District Staff | aaronprussian@fs.fed.us | Sitka, AK
Dennis Landwehr | USFS | Soil Scientist | dlandwehr@fs.fed.us | Ketchikan, AK
Jacquie Foss | USFS | Soil Scientist | jvfoss@fs.fed.us | Sitka, AK
KK Prussian | USFS | Hydrologist | katherineprussian@fs.fed.us | Sitka, AK
Adelaide (Di) Johnson | USFS PNWRS | Hydrologist | ajohnson03@fs.fed.us | Juneau, AK
Dennis Staley | USGS | Research Physical Scientist | dstaley@usgs.gov | Golden, CO
Rex Baum | USGS | Research Geologist | baum@usgs.gov | Golden, CO