## Tasks
Data or Product | Time | Agency | Cost | Comments 2018 | Status 04/05/2019 | Status 09/12/2019
Updated landslide inventory with overlay events | 2017 | USFS (J.F and D.L) | In house |  | Landslide layer has two feature classes, one is a polygon, the other is a best guess of initiation points. Both are available on data.gov | Most recent version is online (data.fs.usda.gov, search by keyword "Tongass") as of ~one month ago.
NetMap (with Miller model) landslide initiation and runout modeling | 2018 | USFS: (D.L., J.F., or A.J.) | $10k (contractor) | Lidar acquision is a prerequisite | Netmap landslide hazard map should be available sometime mid-summer. Terrainworks will build a synthetic stream network and identify confluence zones. The results will be compared with landslide mapping for the area. It will show initiation and runout in one product. | Has been delivered and given a cursory look. It will be shared with the group through the SSSC. There is no comparison between it and Ronnie's map (row 14) because it is preliminary and only being shared for feedback.
Detailed soil maps | 2022 | USFS (J.F) DGGS | No funds identified | Prioritize catchment areas |  | No funding, not a priority.
ArcGIS online app |  | USFS (J.F.) |  |  | Would allow everyone with study sites in Sitka to share locations with each other. | App was built, but still needs work. Difficult to provide access to those without existing accounts.
Soil depth measurements |  | USFS (K.P.), SSSC | $10k (Paid for) |  | Would allow the employment of 2 high school students for field experience. Funds allocated, waiting on approval of agreement. | With SSSC, hired two high school students to collect depth measurements. Acquired 16 depths total in 2/3 of a mile starting from south Kramer slide across the hillslope ~ every 60-100 meters. KK Prussian will send out report
Identify three possible sites for weather station at Gavin or Harbor Mountain | 2017 | USFS: A.Prussian DGGS: G.W. | In house | in progress
Install stream gagues and developing rating curve- Starrigavan and Cascade Cr. | 2017 (S) 2018 (CC) | NWS (A.J.) STA (J.H.) USFS (K.P.) | NWS installation and maintanence ($ TBD) STA personnel to help develop rating curve by taking flow measurements | Need to look at permits from USFS and city to insall gages on bridges before installing | NWS: Starrigavin gauges are up and running, stable as of 04/04/2019. Will be up on the webpage in the next couple of weeks. | Starrigavan gauges have been running all summer long and are available on webpage.
Coupled hydrological/landslide model running in real time | in progress 2023 | NWS (A.J.) DGGS (R.D.) | In house | Research effort hydrological model sooner |  | This probably requires a dedicated person, it will be a great effort.
Install weather station at higher elevation (existing equipment available) | 2018 | DGGS: G.W. USFS: permitting CBS: maintenance | Upgraded: $5k Installation: $20k Maint: $4k/yr | Permitting needed ASAP | USFS: Weather station permitting is nearing completion in conversations with Ronnie, then it's a 6 month processing for permitting. | Weather station installed on Harbor Mountain. Currently collecting data, but not wirelessly reporting. Will be online by end of year.
Targeted repeat laser scans of potential debris-flow source areas | 11/17-5/18 | DGGS/G.W. | Ad hoc if funds available | Repeat at 2-year intervals | Funding required. | Waiting for proper weather window to do this, seeking seeking additional funding to scan some sitka areas (roering contributes 5k, seeking additional 5.5k).
App to involve citizen science for reporting landslides: promotion | 2018 | DGGS (G.W.) SSSC CBS RAND | $5k-$10k | Modified for fishermen/hikers/hunters (Mountain Hub, LEO) | App was purchased by Mammut, put this project on hold. Mammut has accepted the project and this project can continue moving forward. | App issues moving over to Miriam Marlier and Ryan Brown (RAND). Mtnhub app is not going to work, but there seems to be an alternative.
A homewoner's guide to landslides | 2018 | DGGS (G.W./R.D.) CBS (M. Bosak) |  |  | Hasn't been addressed yet, there was pushback until it was funded.
DGGS Hazard Mapping (new lidar from NPS) | 2018 | DGGS/R.D. (USFS) | Paid for | Get boring logs and landslide inventory | Landslide hazard mapping is done, in the hands of the City of Sitka. | Gone though two rounds of internal reviews, currently in the hands of Director Steve Masterman. Next will gro through legal services.
Soil moisture sensors and monitoring (radio network) (Research) | 2019 | USGS (R.B.) DGGS USFS/PNWRS (A.J., J.F.) | $117k equipment. Labor, maintainance, and monitoring extra | Source location in initiation zone (water table) three hollows |  | Still planning to install soil moisture sensors and rain gauge on harbor mountain near UO site. These will be used to compare UO's cheaper sensors to traditional sensors. Data should be available on webpage once reliable (on landslide monitoring page)
Create rainfall intensity and duration curves for existing information | 2018 | NWS (A.J.) USGS (R.B.) USFS (K.P.) | In house | Add smaller slides to inventory slides (USFS) | Completed prelim. looking at data (slides from FS database, events described by Jacquie and others). Put together prelim intensity duration threshold and plans to return to it this summer. | Acquired some additional data, aplnong on working on it this fall. A student is coming in that can devote time to it and a preliminary report should be available before the end of the year.
Establish rainfall runoff (stream gauge) rating curves for Indian River | 2019 | NPS (B.C.) USGS, NWS (A.J.), STA (J.H.) | USGS contracted by NPS | USGS has a published rate curve for Indian River |  | Completed, USGS was able to develop a rating curve. Working on forecast for Indian River.
Real time SNOTEL - ask NRCS (could be higher priority if available) | 2018 | NPS (B.C.) NWS (A.J.), USFS DGGS (G.W.) | $35k install- maintainance TBD | Indian River head waters, permitting USFS
Improve radar use from Biorka flash flood monitoring program | 2019 | NWS (A.J.) | In house |  | New shape files along with improved Flash Flood threshold guidance. This will improve forecaster situational awareness of higher threat of debris flows taking place. Looking to improve the quantitative precipitation estimates from the radar from different Z/R schemes and ground truth from insitu weather stations there are 3 currently but will be 4 after the one gets installed this summer | Working on shape files for internal usage for forecasters. Once weather stations are online, we can start comparing rainfall throughout area.
Gather local people with knowledge of previous landslides (contractors, city crew, journalist) | 2018 | SSSC (L.B.) RAND USFS (A.J.) S&W (B.L.) | ? | Landslide deposition locations |  | Beginning oral history; interested in traditional knowledge, communication channels and influencers, and inclusiong on Tlingit on landslide warning system.
Three additional weather stations |  | DGGS, NWS, CBS | $50kx3 = $150k | Do permitting now |  | Stations are available for donation, but no funds for deployment. Funds require travel to sitka (4-5k), possible helicopter time (if coast guard cannot get involved, 3hrs, 5k)
Blue lake height and connecting NWS | 2018 | CSB (D. Tadic) NWS |  | IT folks
Installing soil moisture sensors |  | UO (J.R., A. Patton) |  |  | Field campaign in June 2019 to begin installation, return in September 2019 | Installed antennas at FS and police station. Sensor node on each mountain (Harbor, Gavan, Verstovia). Batteries not lasting, prepping external battery to last many months. Storm collected from a couple weeks ago, looking at soil moisture response from that. Will be supplementing the existing sensors with 9 additional sensors.
Geologic Mapping | 2019 | UO (A. Patton)
Spatial Patterns from Slope Stability Model | 2019 | UO (E.O.) |  |  |  | Looking at spatial patterns of slides, appears to be interesting patterns
Runout behaviors | 2019 | PSU (A.B., B.V.) |  |  |  | Examined 15-20 slides that happened in 2015, collected deposit area and volume, inundated x-sec, and more. Will share locations and data with KK and Jacquie with FS, and Bryce (student) will share map of Indian River catchment through SSSC
| 2019 | UC Denver (K.T.) |  |  |  | 44 plots in Indian River collecting biomass and soil depth measurements with horizon thickness.

## Contacts
Name | Agency | Title | Email | Location
Megan Bosak | CBS | Community Affairs Director | maegan.bosak@cityofsitka.org | Sitka, AK
Michael Harmon | CBS | Director Public Works | michael@cityofsitka.com | Sitka, AK
Cliff Richter | CBS | City Engineer | cliff.richter@cityofsitka.org | Sitka, AK
Gabriel Wolken | DGGS | Research Scientist | gabriel.wolken@alaska.gov | Fairbanks, AK
Ronald Daanen | DGGS | Geohydrologist | ronald.daanen@alaska.gov | Fairbanks, AK
Chad Hults | NPS | Alaska Regional Geologist | chad_hults@nps.gov | Anchorage, AK
Brinnen Carter | NPS, Sitka | Chief of Natural Resources | brinnen_carter@nps.gov | Sitka, AK
Aaron Jacobs | NWS | Senior Service Hydrologist | aaron.jacobs@noaa.gov | Juneau, AK
Joel Curtis | NWS | Warning Coordination Meteorologist | joel.curtis@noaa.gov | Juneau, AK
Adam Booth | Portland State University | Professor | boothad@pdx.edu | Portland, OR
Bryce Vascik | Portland State University | Grad Student of Adam Booth | bvascik@pdx.edu | Portland, OR
Miriam Marlier | RAND | Associated Physical Scientist | mmarlier@rand.org | Santa Monica, CA
Robert Lempert | RAND | Policy Analyst | lempert@rand.org | Santa Monica, CA
Ryan Brown | RAND | Senior Social and Behavioral Researcher | rbrown@rand.org | Santa Monica, CA
Bill Laprade | Shannon & Wilson | Vide-President | wtl@shanwil.com | Seattle, WA
Lisa Busch | SSSC | Executive Director | lbusch@sitkascience.org | Sitka, AK
Cora Siebert | SSSC | Geoscience Coordinator | csiebert@sitkascience.org | Sitka, AK
Anne Davis | STA | Administrative Services Director | anne.davis@sitkatribe-nsn.gov | Sitka, AK
Jeff Feldspauch | STA | Resources Protection Director | jeff.feldspauch@sitkatribe-nsn.gov | Sitka, AK
Jenn Hamblen | STA | Fishery Biologist | jennifer.hamblen@sitkatribe-nsn.gov | Sitka, AK
Joe Trainor | Udel DRC | Program Director | jtrainor@udel.edu
Brian Buma | University of Colorado | Professor, ecology & landscape change | brian.buma@ucdenver.edu | Denver, CO
Kyle Turchick | University of Colorado | Grad Student of Brian Buma | kyle.turchick@ucdenver.edu | Denver, CO
Josh Roering | University of Oregon | Professor | jroering@uoregon.edu | Eugene, OR
Annette Patton | University of Oregon | Post Doc, Geomorphologist | annettep@uoregon.edu | Eugene, OR
Eli Orland | University of Oregon | Graduate Student of Josh Roering | eorland@uoregon.edu | Eugene, OR
Aaron Prussian | USFS | District Staff | aaronprussian@fs.fed.us | Sitka, AK
Dennis Landwehr | USFS | Soil Scientist | dlandwehr@fs.fed.us | Ketchikan, AK
Jacquie Foss | USFS | Soil Scientist | jvfoss@fs.fed.us | Sitka, AK
KK Prussian | USFS | Hydrologist | katherineprussian@fs.fed.us | Sitka, AK
Adelaide (Di) Johnson | USFS PNWRS | Hydrologist | ajohnson03@fs.fed.us | Juneau, AK
Dennis Staley | USGS | Research Physical Scientist | dstaley@usgs.gov | Golden, CO
Rex Baum | USGS | Research Geologist | baum@usgs.gov | Golden, CO
Ben Mirus | USGS | Research Geologist | bbmirus@usgs.gov | Golden, CO
Corina Cerovski-Darriau | USGS | Research Geologist | ccerovski-darriau@usgs.gov | Menlo Park, CA

## Abbreviations
Abbr. | Full
A.B. | Adam Booth
A.J. | Aaron Jacobs
A.Patton | Annette Patton
A.Prussian | Aaron Prussian
B.B. | Brian Buma
B.C. | Brinnen Carter
B.L. | Bill Laprade
B.V. | Bryce Vascik
C.S. | Cora Siebert
CBS | City and Borough of Sitka
D.L. | Dennis Landwehr
DGGS | [Alaska] Division of Geological and Geophysical Surveys
E.O. | Eli Orland
G.W. | Gabe Wolken
J.F. | Jacquie Foss
J.R. | Josh Roering
K.P. | KK Prussian
K.T. | Kyle Turchick
L.B. | Lisa Busch
NPS | National Park Service
NWS | National Weather Service
PSU | Portland State University
R.B. | Rex Baum
R.D. | Ronnie Daanen
RAND | RAND Corporation
SSSC | Sitka Sound Science Center
STA | Sitka Tribe of Alaska
UC | University of Colorado
Udel DRC | University of Deleware Disaster Research Center
UO | University of Oregon
USFS | US Forest Service
USGS | US Geological Survey